## Risks
ID | Risk | Category | Likelihood (1-5) | Impact (1-5) | Score | Rating | Mitigation | Owner | Status
R-01 | Staff continue using paper/manual inatke | Adoption | 4 | 5 | 20 | Critical | Use staff feedback, workflow observation, and targeted support to identify and address adoption barriers | PC + COL | High priority
R-02 | Workflow changes create additional work or delays in check-in | Operational | 3 | 5 | 15 | High | Validate proposed changes with frontline staff before implementaion and monitor check-in time during the pilot | COL + CAR | In progress
R-03 | Insufficient training/ support | People | 4 | 4 | 16 | High | Develop role-specific guidance and monitor staff-reported confidence during pilot | PC + CAR | Open
R-04 | Patients struggle with digital intake | Adoption | 3 | 4 | 12 | High | Identify patient-facing friction points and retain an appropriate assisted process during the pilot | COL + CAR | In progress
R-05 | Duplicate/manual data entry persists | Operational | 3 | 4 | 12 | High | Track duplicate manual re-entry and investigate recurring workflow or technical causes with IT | PC + IT | In progress
R-06 | Limited staff availability for feedback | People | 3 | 3 | 9 | Medium | Schedule short, targeted feedback sessions and use representatives from affected roles | PC + CAR | Validated
R-07 | Inconsistent KPI data limits comparison | Data | 3 | 4 | 12 | High | Define KPI measurement rules before monitoring and use consistent reporting throughout the pilot | PC | In progress
R-08 | Adoption declines after pilot closeout | Sustainability | 3 | 5 | 15 | High | Assess remaining barriers and provide leadership with specific continuation, ownership, and monitoring recommendations | PC + ES | Open
Risk Rating
Low: 1-4
Medium: 5-9
High: 10-16
Critical: 17-25
RISK REGISTER

## AID log
ID | Type | Description | Impact | Action | Owner | Status
A-01 | Assumption | Existing digital intake workflow remains available during the pilot | High | Confirm availability before pilot | IT | Validated
A-02 | Assumption | Staff representatives are available for workflow validation and feedback | Medium | Confirm representatives and availability | COL + PC | Validated
A-03 | Assumption | Baseline and pilot data can be collected using consistent KPI definitions | High | Finalize KPI measurement rules | PC | In progress
A-04 | Assumption | Clinic leadership supports the proposed workflow changes | High | Confirm approval before implementation | COL + ES | Validated
I-01 | Issue | Staff feedback identified friction in the revised intake workflow | High | Review feedback and prioritize workflow adjustment | COL + PC | In progress
I-02 | Issue | Manual re-entry remained after digital submission | High | Trace workflow and identify source of re-entry | IT + PC | In progress
I-03 | Issue | Staff confidence varied across roles | Medium | Provide targeted guidance and reassess confidence | CAR + PC | In progress
I-04 | Issue | Some patients required additional assistance with digital intake | Medium | Identify common friction points and refine support approach | COL + CAR | Open
D-01 | Dependency | Pilot workflow changes require IT support | High | Confirm IT availability | COL + IT | Validated
D-02 | Dependency | KPI monitoring requires consistent adoption and check-in data | High | Confirm data collection approach | PC | In progress
D-03 | Dependency | Workflow validation requires participation from frontline representatives | Medium | Confirm staff availability | PC + COL | Validated
D-04 | Dependency | Executive recommendations depend on validated pilot findings | High | Confirm KPI results and staff feedback are available | PC + ES | Open
Assumptions, Issues and Dependencies